## Slide 1
CARES Implementation Phase
Rollout #4 PTAX Bi-Weekly Touch Point
April 9, 2025

## Slide 2: Agenda
Schedule Review
Workflows Progress
End-to-End Testing Update
User Acceptance Testing Planning
Action Items Update
Comments/Questions
AGO Collections modernization initiative

## Slide 3: Schedule Review
We are here

## Slide 4: Non-Technical Workflows
Design Session | AGO Owner | Dates Held | Comments
OIC Custom View | Nicole Brock; Kevin Whitacre | 12/5/2024-12/17/2024 | Deployed to AGO QA for testing
WF-49 Tax Memos | Sharnee Jennings/Nick Yono | 1/7/2025 | In testing with C&R
AC-16 Unclaimed Funds | Pat Brobeck, Alison Archer | 2/18/2025 – 3/7/2025 | In development with C&R

## Slide 5: Technical Workflows
Design Session | AGO Owner | Dates Held | Comments
Migration Discussions | Billy Miller, Timothy Greene | 7/29/2024-Present | Ongoing Migration discussions taking place; 7th iterative load has been completed and results are currently under review.
True Up Webservice | Sharnee Jennings, Nick Yono | 9/17/2024 – Present | Development completed by Taxation; currently in testing phase with Taxation business testing completed. Awaiting End-to-End validations.
TCE – Tax Transaction Clean-Up ETL (AGO Internal) | Sharnee Jennings, Nick Yono | 2/6/2025 – 3/7/2025 | In development with C&R
TCI – Trustee Check Interface | Trish Lazich, Kevin Whitacre | 2/25/2025 – 3/6/2025 | In development with C&R
UFI – Unclaimed Funds Inbound | Pat Brobeck | 2/18/2025 – 3/7/2025 | In development with C&R

## Slide 6: End-to-End (E2E) Testing
Targeted start date: 3/10/2025 | Targeted end date: 5/19/2025
Items to be tested with Taxation
Inbound (Taxation AGO) Outbound (AGO Taxation)
File Name | Projected E2E Start Date
XCI – Cert 9020 | 3/10/2025
XNI – NonFinancial 9011.40 | 3/17/2025
XDI – Decert 9407.40 | 3/19/2025
XFI – Transaction Import 9011 | 3/20/2025
XAI – Address Update 9008 | 4/2/2025
File Name | Projected E2E Start Date
XFO – Transaction Export (IB.8050) | 4/4/2025
XNFO – NonFin Export (IB.8050.40) | 4/7/2025
XADO – Tax Archive DataExtract (8050.98) | 4/7/2025
File Name | Projected E2E Start Date
True Up Web Service (Real-Time API call) | 4/2/2025

## Slide 7: E2E Testing: Status Update (Cycle 1)
Interface | Start Date | Status
XCI – Cert 9020 | 3/10/2025 | Completed
XNI – NonFinancial 9011.40 | 3/14/2025 | Completed
XDI – Decert 9407.40 | 3/14/2025 | Completed
XFI – Transaction Import 9011 | 3/20/2025 | Completed
XAI – Address Update 9008 | 3/28/2025 | Completed
XFO – Transaction Export (IB.8050) | 4/4/2025 | In progress
XNFO – NonFin Export (IB.8050.40) | 4/7/2025 | In progress
XADO – Tax Archive DataExtract (8050.98) | 4/7/2025 | In progress
True Up Web Service (Real-Time API call) | 4/2/2025 | Completed

## Slide 8: User Acceptance Testing Planning
Inbound Interfaces | Expected date to get file | Start date | End Date | Number of accounts requested
XAI - Address Update 9008 | TBD | 5/19/2025 | 7/18/2025 | TBD
XFI - Transaction Import 9011 | TBD | 5/19/2025 | 7/18/2025 | TBD
XNI - NonFinancial 9011.40 | TBD | 5/19/2025 | 7/18/2025 | TBD
XCI - Cert 9020 | TBD | 5/19/2025 | 7/18/2025 | TBD
XDI - Decert 9407.40 | TBD | 5/19/2025 | 7/18/2025 | TBD
Outbound Interfaces |  |  |  | 
XFO - Transaction Export (IB.8050) | TBD | 5/19/2025 | 7/18/2025 | TBD
XNFO - NonFin Export (IB.8050.40) | TBD | 5/19/2025 | 7/18/2025 | TBD
XADO - Tax Archive DATAEXTRACT 8050.98 | TBD | 5/19/2025 | 7/18/2025 | TBD
True Up Web Service (API Call) | TBD | 5/19/2025 | 7/18/2025 | TBD
FitPortal Account Validations | TBD | 5/19/2025 | 7/18/2025 | TBD
FitPortal Report Validations | TBD | 5/19/2025 | 7/18/2025 | TBD
Invoicing Validations | TBD | 5/19/2025 | 7/18/2025 | TBD
Phase 1: 5/19/2025 – 7/18/2025 | Phase 2: 7/19/2025 – 8/1/2025

## Slide 9: Action Items
Action Item | Responsible Party | Status
ITSEC01 Form for Service Account | Taxation (Kelly) | Completed
Production URL to Taxation | AGO ITS | Completed
ITSEC03 Forms for E2E and UAT (Completed)/Production | Taxation (Kelly) | In progress
True Up Web Service development | Taxation (Chris B.) | Completed
True Up Web Service testing | Taxation/AGO QA | Completed
File programming changes for R4 development items | Taxation | Completed
End-to-End System testing – Inbound Files | Taxation | Completed
End-to-End System testing – Outbound Files | C&R/AGO QA | In progress
Finalize User Acceptance Testing scenarios | Taxation/AGO UAT | In progress
Establish Communication Process for External UAT Status and Defect Reporting | AGO UAT/AGO ITS | Completed

## Slide 10: Comments/Questions

## Slide 11
Thank You!